## Sprint Plan
CloudFuze AI Governance — Sprint Plan (Jul 29 – Sep 2, 2026)
14 Features │ 2 Developers │ AI-Driven SDLC: Spec → Test → Build → Verify │ No weekends │ No crunch
# | Date Range | Days | Dev | Feature(s) | Description | Status
▁ DAY 0 — HARNESS SETUP (Foundation)
1 | Jul 29 (Tue) | 1 | Dev 1 | Harness Setup — Conventions & Rules | Set up shared coding conventions (API format, error handling, DB naming, React component patterns). Update CLAUDE.md with rules for all feature areas. Create feature spec template. Define API contract schema for all new routes. | Not Started
2 | Jul 29 (Tue) | 1 | Dev 2 | Harness Setup — Test & UI Infrastructure | Set up test harness (runner, fixtures, mock data, test DB seeding). Create shared UI patterns (dashboard template, chart components, tables, filters). Set up DB migration workflow with rollback. Wire CI feedback loop. | Not Started
▁ BLOCK 1 — GUARDRAILS (#3) + AGENT TRACING (#2) [Jul 30 – Aug 5]
3 | Jul 30 (Wed) | 1 | Dev 1 | #3 Guardrails — SPEC & TESTS | Write guardrails architecture spec: pluggable pipeline, GuardrailProvider interface, result schema, threshold config. Write 250+ test prompts across 5 detector types (injection, jailbreak, hallucination, toxicity, bias) with expected pass/fail outcomes. | Not Started
4 | Jul 30 (Wed) | 1 | Dev 2 | #2 Tracing — SPEC & TESTS | Write tracing architecture spec: hierarchy (app > session > agent > trace > span), 5 span types, capture strategy, WebSocket streaming protocol. Write tests for trace ingestion, span ordering, hierarchy queries, API endpoints. | Not Started
5 | Jul 31 (Thu) | 1 | Dev 1 | #3 Guardrails — BUILD Detectors (1/2) | Conductor mode: build pipeline architecture + Prompt Injection detector (pattern-based context overrides, role injection) + Jailbreak detector (DAN/STAN patterns, base64/ROT13 encoding bypass, character substitution). Run tests after each. | Not Started
6 | Jul 31 (Thu) | 1 | Dev 2 | #2 Tracing — BUILD Backend + API | Build trace data model + DB migrations, capture engine (HTTP header correlation, auto-instrumentation from proxy), REST API (CRUD traces/spans, query by app/session/agent, filter by time/status/type). Run tests. | Not Started
7 | Aug 1 (Fri) | 1 | Dev 1 | #3 Guardrails — BUILD Detectors (2/2) | Build Hallucination detector (grounding check, URL validation, confidence scoring) + Toxicity detector (multi-category: hate, violence, harassment, self-harm) + Bias detector (protected characteristics, stereotyping patterns, sentiment analysis). | Not Started
8 | Aug 1 (Fri) | 1 | Dev 2 | #2 Tracing — BUILD Timeline UI | Build Gantt-style timeline (horizontal bars per span, color-coded by type, nested parent-child, hover popup with prompt/response/latency/tokens/cost). Multi-level trace browser with 4-level drill-down (app > session > agent > trace). | Not Started
9 | Aug 4 (Mon) | 1 | Dev 1 | #3 Guardrails — BUILD Integration + Dashboard | Wire 5 detectors into proxy + desktop hook + browser extension + MCP guard. Build dashboard (violation heatmap, trend lines, top offenders, drill-down). Build alert engine (configurable rules, webhook/email notifications, 5-min batching). | Not Started
10 | Aug 4 (Mon) | 1 | Dev 2 | #2 Tracing — BUILD Live Streaming + Metrics | Build WebSocket live streaming (real-time span updates, auto-scroll, running timer on open spans, <100ms latency). Build metrics panel (P50/P95/P99 latency per span type, success/failure rates, token usage, cost per span). | Not Started
11 | Aug 5 (Tue) | 1 | Dev 1 | #3 Guardrails — VERIFY | Run 250+ test cases across all 5 detectors and all 4 enforcement surfaces. Tune confidence thresholds. Fix false positives (code "kill process" is not violence). Performance: confirm <100ms latency overhead. The "20%" day. | Not Started
12 | Aug 5 (Tue) | 1 | Dev 2 | #2 Tracing — VERIFY | Ingest traces from proxy traffic, verify timeline renders. Test live streaming latency. Test 4-level drill-down. Stress test with 1000+ spans. Fix rendering bugs and data consistency issues. The "20%" day. | Not Started
▁ BLOCK 2 — REPLAY (#16) + ROUTING (#5) ¦ SPEND (#10) + ATTRIBUTION (#13) [Aug 6 – 12]
13 | Aug 6 (Wed) | 1 | Dev 1 | #16 Session Replay — SPEC + BUILD | Spec extends tracing with full content storage (prompt + response text + file uploads per exchange). Build session capture engine + replay player UI (chronological chat view, timestamps, guardrail markers inline, scroll controls). | Not Started
14 | Aug 6 (Wed) | 1 | Dev 2 | #10 Spend Caps — SPEC + BUILD Backend | Spec: budget model (entity, limit_usd, period, cap_type), enforcement logic, alert thresholds, override mechanism. Build budget engine + enforcement middleware (auto-reject at limit with HTTP 429) + tiered alerts (50/75/90/100%). | Not Started
15 | Aug 7 (Thu) | 1 | Dev 1 | #16 Session Replay — BUILD Export + VERIFY | Build forensic export (signed JSON + PDF evidence package with full session, timestamps, guardrail events, integrity hash). Verify: replay accuracy, export hash verifies, guardrail events highlighted, PDF renders cleanly. | Not Started
16 | Aug 7 (Thu) | 1 | Dev 2 | #10 Spend Caps — BUILD Dashboard + VERIFY | Build admin override with audit trail + budget dashboard (utilization bars, create/edit, alert history, projected exhaustion) + chargeback report (PDF/CSV). Verify: set budget, trigger alerts at thresholds, confirm block at limit, test override. | Not Started
17 | Aug 8 (Fri) | 1 | Dev 1 | #5 Model Routing — SPEC & TESTS | Write routing spec: engine architecture, 4 strategies (cost-based, sensitivity-based, compliance-based, failover), load balancer, health checker, rule schema. Write tests for 20+ routing scenarios, failover behavior, cost savings calculation. | Not Started
18 | Aug 8 (Fri) | 1 | Dev 2 | #13 Attribution — SPEC + BUILD Backend | Spec: cost calculator (token x model pricing per provider), per-request user attribution via enrollment identity, forecast algorithm. Build cost calc engine + per-request attribution + running totals + 90-day history. | Not Started
19 | Aug 11 (Mon) | 1 | Dev 1 | #5 Model Routing — BUILD Engine | Conductor mode: build routing engine + 4 strategies (simple to cheap model, PII to private model, EU data to EU endpoint, auto-failover on errors) + weighted load balancer + health checker + proxy integration. Run tests per strategy. | Not Started
20 | Aug 11 (Mon) | 1 | Dev 2 | #13 Attribution — BUILD Dashboard | Build attribution dashboard: executive view (total by dept), team view (per-person), individual self-service view, tool view (cost by AI service). Build forecast engine, spend leaderboard, cost optimization suggestions. | Not Started
21 | Aug 12 (Tue) | 1 | Dev 1 | #5 Model Routing — BUILD Dashboard + VERIFY | Build rule builder UI, rule testing ("paste prompt, see route"), routing analytics (traffic distribution, cost savings, latency comparison, failover log). Verify: all 4 strategies live, simulate endpoint failure, validate savings math. | Not Started
22 | Aug 12 (Tue) | 1 | Dev 2 | #13 Attribution — VERIFY | Verify: cost numbers match actual provider pricing for OpenAI/Anthropic/Google. Forecast accuracy vs. historical data. All dashboard views render correctly. Leaderboard ranks correctly. Chargeback report matches spend cap data. | Not Started
▁ BLOCK 3 — POLICY PACKS (#11) + TOKENIZATION (#6) ¦ RISK SCORE (#24) + SIMULATOR (#25) [Aug 13 – 18]
23 | Aug 13 (Wed) | 1 | Dev 1 | #11 Policy Packs — SPEC + Framework | Spec: PolicyPack model (name, framework, version, rules[]), one-click deploy engine, per-rule customization, versioning. Build pack framework. Start GDPR pack (20+ rules) as reference implementation. | Not Started
24 | Aug 13 (Wed) | 1 | Dev 2 | #6 PII Tokenization — SPEC + BUILD Engine | Spec: tokenizer architecture (PII detect, replace with [PERSON_a1b2] tokens), token store (secure, per-request, local only), de-tokenization flow. Build tokenizer + token store + de-tokenizer. Tests: 5 PII types, round-trip accuracy. | Not Started
25 | Aug 14 (Thu) | 1 | Dev 1 | #11 Policy Packs — BUILD 3 Packs | Orchestrator mode: GDPR pack (20+ rules: PII detection, data residency, consent, minimization) + HIPAA pack (15+ rules: 18 PHI identifiers, BAA enforcement, audit logging) + SOC 2 pack (12+ rules: access controls, monitoring, change mgmt). | Not Started
26 | Aug 14 (Thu) | 1 | Dev 2 | #6 PII Tokenization — Integration + VERIFY | Wire into proxy (tokenize before send, de-tokenize after receive). Verify: prompt with 5 PII types, all tokenized, AI responds with tokens, de-tokenized correctly for user. Confirm original PII never leaves CloudFuze server. | Not Started
27 | Aug 15 (Fri) | 1 | Dev 1 | #11 Policy Packs — BUILD 3 More + Dashboard | CCPA pack (10+ rules) + EU AI Act pack (15+ rules) + ISO 42001 pack (12+ rules). Build pack management dashboard (browser, active packs, health view, rule toggles, cross-pack comparison). Total: 100+ rules across 6 packs. | Not Started
28 | Aug 15 (Fri) | 1 | Dev 2 | #24 Risk Score — Full BUILD + VERIFY | Scoring formula: tool usage 20%, sensitivity 25%, guardrail violations 30%, volume anomalies 15%, compliance 10%. Ranges: 0-30 Low, 31-60 Med, 61-80 High, 81-100 Critical. Build engine + cron + dashboard (cards, distribution, trending, manager view). Verify against profiles. | Not Started
29 | Aug 18 (Mon) | 1 | Dev 1 | #11 Policy Packs — VERIFY | Deploy each of 6 packs. Verify all 100+ rules fire correctly. Test individual rule toggling. Test pack health calculation. Test cross-pack overlap detection. Regression test against existing DLP rules. The "20%" day for policy packs. | Not Started
30 | Aug 18 (Mon) | 1 | Dev 2 | #25 Policy Simulator — Full BUILD + VERIFY | Simulation engine replays last 30 days of events against proposed rules. Build results UI (total blocks, affected users, tool breakdown, sample events, productivity impact, side-by-side comparison). Verify simulation matches manual calculation. | Not Started
▁ BLOCK 4 — INCIDENT RESPONSE (#28) + COMPRESSION (#18) ¦ COPILOT READINESS (#17) [Aug 19 – 22]
31 | Aug 19 (Tue) | 1 | Dev 1 | #28 Incident Response — SPEC + BUILD | Spec: workflow (detect > create ticket > assign > escalate > resolve > close), Jira/ServiceNow webhook, escalation timers, routing rules. Build workflow engine + Jira webhook + escalation timer + auto-assignment based on violation type. | Not Started
32 | Aug 19 (Tue) | 1 | Dev 2 | #17 Copilot Readiness — SPEC & TESTS | Spec: MS Graph API plan (OAuth, scopes: Sites.Read.All, Files.Read.All, Team.ReadBasic.All), SharePoint/OneDrive/Teams permission enumeration endpoints. Analysis algorithm for "overshared" detection. Report format with remediation steps. | Not Started
33 | Aug 20 (Wed) | 1 | Dev 1 | #28 Incident Response — Dashboard + VERIFY | Build incident dashboard (open incidents, SLA tracking, MTTR metrics) + investigation tools (links to session replay, risk score, event context) + resolution tracking. Verify: trigger violation, verify Jira ticket created, verify escalation fires. | Not Started
34 | Aug 20 (Wed) | 1 | Dev 2 | #17 Copilot Readiness — BUILD MS API | Conductor mode: Azure AD app registration + OAuth consent flow + MS Graph API client. Build SharePoint site permission enumeration (detect "Everyone" access on sensitive document libraries and sites). | Not Started
35 | Aug 21 (Thu) | 1 | Dev 1 | #18 Token Compression — SPEC + BUILD | Spec: system prompt dedup (hash + cache), context compression (filler removal), KV cache alignment. Build compression engine + cache layer + proxy integration (intercept, compress, forward, track savings). | Not Started
36 | Aug 21 (Thu) | 1 | Dev 2 | #17 Copilot Readiness — BUILD Analysis | Build OneDrive shared folder analysis + Teams public channel scan + Exchange delegate access check. Build analysis engine with risk scoring per finding and severity classification (Critical/High/Medium/Low). | Not Started
37 | Aug 22 (Fri) | 1 | Dev 1 | #18 Token Compression — Dashboard + VERIFY | Build savings dashboard (tokens saved, dollars saved, compression ratio). Verify: 100 identical system prompts deduplicated, response quality unchanged, savings numbers accurate. Confirm no behavior change for end users. | Not Started
38 | Aug 22 (Fri) | 1 | Dev 2 | #17 Copilot Readiness — Report + VERIFY | Build remediation report generator (step-by-step fix per finding) + dashboard UI (findings list, severity badges, exposure count, remediation checklist). Verify against test MS tenant: findings accurate, report generates, remediation steps actionable. | Not Started
▁ BLOCK 5 — DEVELOPER SDK (#14) + INTEGRATION TESTING [Aug 25 – 26]
39 | Aug 25 (Mon) | 1 | Dev 1 | #14 Developer SDK — Full BUILD | Build @cloudfuze/sdk npm package. Auto-instrumentation: require("@cloudfuze/sdk").instrument() patches OpenAI + Anthropic create methods. Auto-reports traces, tokens, cost, latency. LangChain callback handler. TypeScript types. README + quickstart. | Not Started
40 | Aug 25 (Mon) | 1 | Dev 2 | Cross-Feature Integration Testing (1/2) | Test interactions: guardrail violations feed into risk scores. Policy packs work with simulator. Tracing + replay show consistent data. Spend caps + attribution numbers match. Routing + tokenization work together at proxy layer. | Not Started
41 | Aug 26 (Tue) | 1 | Dev 1 | #14 Developer SDK — VERIFY | Test with real OpenAI + Anthropic calls: add 1 line to Node.js app, verify calls appear in tracing + cost dashboards. Verify guardrails run on SDK calls. Confirm SDK does not leak API keys or break existing app behavior. | Not Started
42 | Aug 26 (Tue) | 1 | Dev 2 | Cross-Feature Integration Testing (2/2) | Test: SDK data flows into tracing. Compression savings in cost analytics. Copilot report generates end-to-end. Incident workflow triggers from guardrail violations. Compression does not break tokenization pipeline. | Not Started
▁ BLOCK 6 — FINAL VERIFICATION + DEMO READINESS [Aug 27 – 29]
43 | Aug 27 (Wed) | 1 | Dev 1 | Edge Case Testing | Test: budget at $0.01, 50 concurrent guardrail checks, nested PII tokenization, routing with all endpoints down, compression of 1-token prompt, risk score for zero-activity user, simulator with empty history, single-message replay. | Not Started
44 | Aug 27 (Wed) | 1 | Dev 2 | Performance Testing | Benchmark: guardrails <100ms p95, tracing 1000+ spans/sec, routing <50ms, tokenization round-trip, WebSocket <100ms, policy pack deploy time, compression ratio by request type. Identify and fix bottlenecks. | Not Started
45 | Aug 28 (Thu) | 1 | Dev 1 | Security Review | Audit: tokenization never leaks originals in logs/errors, audit data integrity, SDK never exposes API keys, Copilot OAuth scopes minimal, no injection vectors in policy rules, no XSS in dashboard inputs, no SQL injection in query params. | Not Started
46 | Aug 28 (Thu) | 1 | Dev 2 | Bug Fix Sprint | Fix all issues from edge case, performance, and security testing. Re-test each fix. Full regression across all 14 features. Confirm zero regressions introduced by fixes. | Not Started
47 | Aug 29 (Fri) | 1 | Dev 1 | Demo Data Seeding | Create realistic dataset: 30 days of AI usage, 200 users, 15 teams, 10K+ events, guardrail violations, budget alerts, traces with spans, risk scores, incidents, routing savings, compression metrics. Every dashboard looks compelling. | Not Started
48 | Aug 29 (Fri) | 1 | Dev 2 | Demo Scenario Scripting | Script 4 walkthroughs: (1) Security Incident — jailbreak > guardrail > incident > replay (2) Cost Optimizer — spend > routing > compression (3) Compliance Officer — packs > simulator > Copilot (4) Data Protector — tokenization > SDK > trace. | Not Started
▁ BUFFER — OPTIONAL [Sep 1 – 2]
49 | Sep 1 – 2 | 2 | Both | Buffer / Polish | Available if any feature needs extra time. If not needed: additional demo polish, documentation, sales enablement materials, or head-start on next feature cycle. Zero pressure — this is insurance, not obligation. | Not Started
▁ SUMMARY
| Total Working Days |  | 24 + 2 buffer = 26
| Developers |  | 2 working in parallel tracks
| Features Delivered |  | 14 production-quality features
| Methodology |  | AI-Driven SDLC: Spec → Test → Build → Verify
| Weekend Work |  | None required
| Estimated Completion |  | Aug 29 (buffer through Sep 2)
| Compliance Packs |  | 6 packs with 100+ rules (GDPR, HIPAA, SOC 2, CCPA, EU AI Act, ISO 42001)
| Guardrail Types |  | 5 (prompt injection, jailbreak, hallucination, toxicity, bias)